## Sheet1
2017 Annual Plan: Activities
Broad Activity | Proposed Activities | Specific activities | Q1 | Q2 | Q3 | Q4 | Lead | Support
Strategic Objective 1: Fund policies, processes, structures, and effectiveness improve as a result of Aidspan’s critical assessment
1.1 Effectiveness of funding processes, assurance mechanisms, and governance and management structures at global and country levels. | 1.1.1 Assess the Fund’s global-level operations, structures and processes, including assurance mechanisms, and their impact on country level operations | Assess usefulness of Budget modules in improvng transparency and ability by extenal/independent actors to track costs of supported programmes Track Global Fund’s engaement/ support of community monitoring systems and national oversight bodies in identifying and mitigating risks | X | X | X | X | SE | CO/ED
| 1.1.2 Examine effectiveness of funding processes, from concept development through to TRP and GAC reviews, grant-making, approvals and disbursements. | Evaluate grant management systems and processes, including concept note reviews, grant negotiations timeliness of grant approvals and disbursements | X | X | X | X
| 1.1.3 Assess extent to which country level oversight bodies enhance effectiveness and accountability | In 5 countries assess the role played by national oversight bodies in ensuring and proving value for money of Global Fund investments - and how this links to effective effective risk identification and mitigation |  | X | X | X
| 1.1.4 Assess effectiveness of measures the fund uses to measure its performance | Explore effectiveness of the Fund's Key Performance Indicators (KPIs) in enhancing grant performance. Assess how the Fund identifies and understands its results - how realistic are they? | X | X | X | X
| 1.1.5 Assess the effectiveness of the Fund’s procurement-related policies and their implementation | Track Value for Money of Fund's Pooled Procurement and its impact on national procurement systems; | X | X | X | X |  | SPA
| 1.1.6 Assess the impact of Global Fund policies on strengthening national health systems. | Investigate effects the Funding Model has had on the concept of country ownership Assess community health systems accountabilty frameworks in 5 countries, identify opportunities to document Assessing GF's investment in health systems? How did it work? How is it currently working? | X | X | X |  |  | CE/SPA
1.2 Contribution of the Fund to sustaining impact in countries transitioning from Global Fund financing. | 1.2.1 Assess the strategy and policies the Fund adopts with respect to its role in the development and implementation of transition planning. | Investigate /get case syudies of where transition planning has worked, or failed miserably. |  | X | X |  | SPA | CE/ED
| 1.2.2 Investigate the impact of Global Fund withdrawal from supported countries, particularly on key affected populations | Get evidence of changes in service quality in countries transitioning away from Global Fund finanacing (Integrate this with 121 above) |  | X | X
1.3 Effectiveness of policies and processes in enhancing involvement of key populations in country-level processes, the response to gender inequalities and violence, and the attention to human rights issues in the response to the three diseases. | 1.3.1 Investigate the measures taken by the Fund to ensure that its grants enhance the rights of key affected populations including children and young people. | 5 country analyses –assess approved concept notes in planning for human rights programs and usefulness for KAPs (to be defined) | X | X |  |  | SPA | CO/ED
| 1.3.2 Assess the measures taken by the Fund to ensure that its grants enhance the response to gender inequalities and violence against women. | Develop periodic policy reviews/briefs Track GF Funding to commercial sex workers and sexual and reproductive health programme, and impact | X | X | X | X
1.4 Effectiveness of the Fund’s role in increasing domestic funding for health as one step towards sustainability. | 1.4.1 Assess the Fund’s efforts to promote increased government funding of national programs to fight the three diseases. | Produce fact sheets/Policy reviews and stakeholder engagements: | X | X | X | X | CO/CE | SPA/ED
Broad Activity | Proposed Activities |  | Q1 | Q2 | Q3 | Q4 | Lead | Support
Strategic Objective 2: Fund becomes more transparent with more accurate and complete data made available
2.1 Extent of transparency with respect to Fund related documents. | 2.1.1 Highlight gaps in information that should be made public by the Fund at all levels. | With select watchdog partners in 7 countries, assess existing community level monitoring networks improve access to country-level data and tracking of Global Fund supported programs Develop tracking and feedback channels for collection of financial, programmatic and performance data of country level implementers Hold thematic round-tables for targeted partners In 4 countries of the above, identify, plan and implement investigative pieces (collaboration: watchdog partners and a media association/ house) |  | X | X | X | SPA/PA | FRM/ED
| 2.1.2 Direct engagement with key global fund offices on remedial action. | Hold regular in-person consultations Involve GF staff in regular thematic round-tables with strategic partners | X | X | X | X
2.2 Availability of quality data at country level for effective grant making and measuring success of Global Fund investments. | 2.2.1 Assess the Fund’s efforts to access quality country level data | Periodic assessments Form strategic alliances with other data users/chasers Data collection from key GF officers and country data sources | X | X | X | X | SE | ED/SPA/PA
2.3 Collaborate with experts and Organizations working on transparency and data quality. | 2.3.1 Increase the breadth and depth of analyses by other agencies regarding Global Fund related transparency and data issues | Use GFO as the primary dissemination channel Improve uptake of users on and improve Aidspan online data portal – the Aidspan portal workbench (APW) and all other public access data tools Peer reviewed publications | X | X | X | X | PA/CO | ED
| 2.3.2 Stimulate demand for transparency and access to quality data by country level stakeholders | Develop a stakeholder engagement strategy Thematic round-tables that feed back into our analyses/ content and that of the partners above(Integrate into thematic round-tables above)
Broad Activity | Proposed Activities |  | Q1 | Q2 | Q3 | Q4 | Lead | Support
Strategic Objective 3: Aidspan becomes stronger and more sustainable
3.1 Improved Board governance and oversight | 3.1.1 Improve Board operations. | Review Board structure Board governance manual Annual Board calendar | X |  |  |  | ED
| 3.1.2 Enhance Board development and performance | Board development plan Annual board performance review Implement a suitable resource mobilization strategy | X | X | X | X
3.2 Strengthen Management sructures, systems and processes | 3.2.1 Enhance Aidspan’s organizational structure | Review Aidspan’s legal identity Implement a suitable resource mobilization strategy | X |  |  |  | SPA/FRM/AAS/ED
| 3.2.2 Attract, retain and develop optimal human resources | Recruitment, review staffing plan, competency; Job evaluation/ profiling, pay structure, staff development Strategic partners –collaborators, consultants, interns, volunteers etc. Develop a technical advisory board – pool of experts called on as needed (Target 2 experts in 2016, 2 more in 2017)(approx. 10 days per expert @ $600/day rate max) | X | X | X | X
| 3.2.3 Improve leadership and management practices | Strengthen the office of the ED Management succession plan Business continuity, risk management | X | X | X | X
| 3.2.4 Establish a robust performance management system | Annual work plans and stricter staff performance management plan Annual board/ management retreats+ Mid-term Review | X | X | X | X
| 3.2.5 Develop information, communication and knowledge management systems | Recruit communications oficer: Build a strong communications and knowledge management unit Improve Aidspan online data portal – the Aidspan portal workbench (APW) and all other public access data tools, highlighting data gaps Update communication strategy Invest in a high caliber digital library and appropriate ICT resources Do 1 annual audience/stakeholder analysis | X | X | X | X
3.3 Efficient mobilizatin of financial resources | 3.3.1 Retain and diversify donor base | Donor engagement strategy Periodic donor profiling and survey Demonstrate our value for money Attend GF board meetings and other relevant workshops and conferences | X | X | X | X | FRM/AAS/ED | PA
| 3.3.2 Enhance operational efficiency | Continue Private Interaction with GF staff and Board Expense management and control Use partner clusters in as much work as possible
3.4 Administration and Human resources | 1. Conduct annual staff performance appraisals 2. Implement a staff training and development plan, 3.Produce monthly, quarterly and annual financial reports including year end audited financials annual budgets 4.Hold regular brown bag meetings and writing retreats 5.Ensure Tax Compliance |  | X | X | X | X | AAS/FRM | OA/RA/ED
Abbreviations
Executive Director | ED
Senior Policy Analyst | SPA
Policy Analyst | PA
Chief Editor | SE
Website & Comm. Officer | CO
Finance & Reporting Manager | FRM
Accounts & Admin Assistant | AAS
Office Assistant | OA